## Slide 1
ERP Modernization — Meeting Minutes
Steering Committee | March 2026
Kebony | ERP Modernization | Steering Committee | March 2026
Project Timeline
Go-live postponed to 1st July 2026 | Project readiness target: 1st June 2026
Campaigning
Scope to be confirmed in April for go-live 01/07/2026
HR & Payroll
Test run: August 2026
Go-live: September 2026
Management Reporting
Data processing latency to be evaluated if reporting is done in Odoo
Full scope (Power BI, MS Fabric) to be confirmed for Q4
Security
Blueprint to be revised to allow for BU + legal entity and country level access
Product Master Data
To be revalidated before go-live
Costing & Manufacturing
Blueprint to be reviewed and validated by CFO
Approval Workflows
Safety error margin (%) on quantity/price discrepancy?
Exceptions to the PO process?
Link with the budgeting process?
GDPR Compliance
To be included in scope
Data structure for reporting to be reviewed

## Slide 2
Actions & Next Steps
Steering Committee | March 2026
Kebony | ERP Modernization | Steering Committee | March 2026
Change Management
Super Key Users to be identified and appointed per workstream
Training plan to be defined once Key Users are confirmed
June testing period dedicated to hands-on validation
Project Management
Olivier & Olga to escalate risks via structured gate-keeping
Signed-off workstream approvals to be introduced
Detailed project timeline to be published (workshops + testing sessions)
Action Items
Owner
Action
Target
Olivier & Olga
Fix and share detailed project timeline
April 2026
Olivier & Olga
Book implementation workshops and testing sessions
April 2026
Olivier & Olga
Introduce gate-keeping / workstream sign-off system
April 2026
Project Team
Confirm campaigning scope for go-live
April 2026
Project Team
Identify and appoint Super Key Users
April 2026
CFO / Finance
Review and validate costing & manufacturing blueprint
April 2026
Project Team
Revalidate product master data
May 2026
Project Team
Revise approval workflow blueprint (margins, exceptions, budget link)
April 2026
Project Team
Include GDPR compliance in scope — review data structure
April 2026