## Overview
Odoo Migration Tracker
BNV + Norway #1 + Norway #2 · Dry-run 01-Jun-2026 · Go-live 01-Jul-2026 · v1.0 · Olivier Eberhard
Use this workbook weekly. Master Tracker drives the call; other tabs are the detail.
WEEKLY DASHBOARD
Workstream | Owner | Target date | % complete | RAG | Blocker | Next milestone | Last updated
P1 — Norway CoA + company setup | [employee] | 2026-05-03 | 0% |  |  | Companies created in staging
Master data (partners / products / taxes / banks) | [employee] | 2026-05-10 | 0% |  |  | Partner + product load signed off
Opening BS (01-Jan-2026) | [employee] | 2026-05-15 | 0% |  |  | TB matches audited close × 3 entities
YTD JEs Jan → May | [employee] | 2026-05-28 | 0% |  |  | ≥4 closed months reconciled
Open AR / AP / PO / SO | [employee] | 2026-05-31 | 0% |  |  | Line-level match vs. legacy
Stock + lots + FIFO cost | [employee] + ops | 2026-05-31 | 0% |  |  | Physical count + valuation recon
Norwegian SPA raw-material lots | [employee] + legal | 2026-05-31 | 0% |  |  | Line-by-line validated with legal
Slow-mover per-lot provision | [dev] | 2026-06-15 | 0% |  |  | Tested on ≥50 lots vs. Excel
SPA unwind transition JE model | Olivier + auditor | 2026-06-15 | 0% |  |  | JE modelled + auditor sign-off
Dry-run pack (01-Jun) | Olivier + employee | 2026-06-01 | 0% |  |  | Sign-off per entity
Change mgmt — auditor | Olivier | 2026-05-15 | 0% |  |  | Written positions received
Change mgmt — tax / customs | Olivier + advisor | 2026-05-01 | 0% |  |  | VAT + Intrastat reviewed
Change mgmt — suppliers | Procurement | 2026-06-01 | 0% |  |  | Notices sent, responses logged
Change mgmt — customers | Sales + Legal | 2026-06-01 | 0% |  |  | Formal notice ≥30d before 01-Jul
Internal training | Employee owner | 2026-06-25 | 0% |  |  | Walk-through completed
MVGL data refresh at 30-Jun | [employee] | 2026-06-30 | 0% |  |  | Go-live-ready snapshot
Go / No-Go decision | Olivier | 2026-06-25 | 0% |  |  | Green / Amber / Red call
Go-live + transition JE (01-Jul) | All | 2026-07-01 | 0% |  |  | Posted in Odoo

## Master Tracker
Master Tracker — task-level execution
One row per task × entity. Update weekly before the Monday call.
ID | Workstream | Entity | Task | Owner | Dependency | Start | Due | Status | % | Evidence / link | Notes
P1.1 | P1 Norway CoA + cie | BNV | Create BNV company in Odoo staging | [employee] | — | 2026-04-22 | 2026-04-24 | Not started | 0%
P1.2 | P1 Norway CoA + cie | NO #1 | Create Norway #1 company in Odoo staging | [employee] | — | 2026-04-22 | 2026-04-24 | Not started | 0%
P1.3 | P1 Norway CoA + cie | NO #2 | Create Norway #2 company in Odoo staging | [employee] | — | 2026-04-22 | 2026-04-24 | Not started | 0%
P1.4 | P1 Norway CoA + cie | BNV | Install Belgian localisation + load CoA | [employee] | P1.1 | 2026-04-24 | 2026-04-28 | Not started | 0%
P1.5 | P1 Norway CoA + cie | NO #1 | Install Norwegian localisation + load CoA | [employee] | P1.2 | 2026-04-24 | 2026-04-28 | Not started | 0%
P1.6 | P1 Norway CoA + cie | NO #2 | Install Norwegian localisation + load CoA | [employee] | P1.3 | 2026-04-24 | 2026-04-28 | Not started | 0%
P1.7 | P1 Norway CoA + cie | All | CoA mapping legacy → Odoo (CSV deliverable) | [employee] | P1.4-6 | 2026-04-28 | 2026-05-01 | Not started | 0%
P1.8 | P1 Norway CoA + cie | All | Configure fiscal year, currency, journals, taxes | [employee] | P1.7 | 2026-05-01 | 2026-05-03 | Not started | 0%
P1.9 | P1 Norway CoA + cie | All | Configure bank accounts + fiscal positions + payment terms | [employee] | P1.8 | 2026-05-01 | 2026-05-03 | Not started | 0%
P1.10 | P1 Norway CoA + cie | All | Security groups: controller / accountant / preparer / read-only | [employee] | P1.8 | 2026-05-01 | 2026-05-03 | Not started | 0%
P1.11 | P1 Norway CoA + cie | All | Dummy JE test per entity + sign-off | Olivier | P1.10 | 2026-05-03 | 2026-05-03 | Not started | 0% |  | Must be complete before §4 starts
MD.1 | Master data | All | Partner extract from legacy (customers + vendors) | [employee] | P1.11 | 2026-05-03 | 2026-05-06 | Not started | 0%
MD.2 | Master data | All | Partner load + VAT / bank / payment terms | [employee] | MD.1 | 2026-05-06 | 2026-05-08 | Not started | 0%
MD.3 | Master data | All | Product extract + category + UoM + FIFO cost | [employee] | P1.11 | 2026-05-03 | 2026-05-06 | Not started | 0%
MD.4 | Master data | All | Product load + lot-tracking flags (FSC/PEFC) | [employee] | MD.3 | 2026-05-06 | 2026-05-10 | Not started | 0%
MD.5 | Master data | All | Analytic accounts / tags | [employee] | P1.11 | 2026-05-06 | 2026-05-10 | Not started | 0%
MD.6 | Master data | All | FX rate table loaded (01-Jan + monthly closes) | [employee] | P1.11 | 2026-05-06 | 2026-05-08 | Not started | 0%
MD.7 | Master data | All | Master data sign-off (controller) | Olivier | MD.2,MD.4,MD.5,MD.6 | 2026-05-10 | 2026-05-10 | Not started | 0%
OB.1 | Opening BS | BNV | Extract TB 01-Jan-2026 | [employee] | MD.7 | 2026-05-10 | 2026-05-12 | Not started | 0%
OB.2 | Opening BS | NO #1 | Extract TB 01-Jan-2026 | [employee] | MD.7 | 2026-05-10 | 2026-05-12 | Not started | 0%
OB.3 | Opening BS | NO #2 | Extract TB 01-Jan-2026 | [employee] | MD.7 | 2026-05-10 | 2026-05-12 | Not started | 0%
OB.4 | Opening BS | All | Post opening JE per entity (balances to retained earnings) | [employee] | OB.1-3 | 2026-05-12 | 2026-05-14 | Not started | 0%
OB.5 | Opening BS | All | Opening BS reconciliation vs. audited close — sign-off | Olivier | OB.4 | 2026-05-14 | 2026-05-15 | Not started | 0%
JE.1 | YTD JEs | All | Extract Jan JEs from legacy (all 3 entities) | [employee] | OB.5 | 2026-05-15 | 2026-05-17 | Not started | 0%
JE.2 | YTD JEs | All | Load + reconcile Jan TB | [employee] | JE.1 | 2026-05-17 | 2026-05-19 | Not started | 0%
JE.3 | YTD JEs | All | Load + reconcile Feb TB | [employee] | JE.2 | 2026-05-19 | 2026-05-21 | Not started | 0%
JE.4 | YTD JEs | All | Load + reconcile Mar TB | [employee] | JE.3 | 2026-05-21 | 2026-05-23 | Not started | 0%
JE.5 | YTD JEs | All | Load + reconcile Apr TB | [employee] | JE.4 | 2026-05-23 | 2026-05-26 | Not started | 0%
JE.6 | YTD JEs | All | Load + reconcile May TB (partial — close mid-month snapshot) | [employee] | JE.5 | 2026-05-26 | 2026-05-28 | Not started | 0%
OI.1 | Open items | All | Extract open AR at 31-May (per invoice) | [employee] | MD.7 | 2026-05-28 | 2026-05-29 | Not started | 0%
OI.2 | Open items | All | Extract open AP at 31-May (per bill) | [employee] | MD.7 | 2026-05-28 | 2026-05-29 | Not started | 0%
OI.3 | Open items | All | Extract open PO at 31-May (per line) | [employee] | MD.7 | 2026-05-28 | 2026-05-29 | Not started | 0%
OI.4 | Open items | All | Extract open SO at 31-May (per line) | [employee] | MD.7 | 2026-05-28 | 2026-05-29 | Not started | 0%
OI.5 | Open items | All | Load AR/AP/PO/SO into Odoo | [employee] | OI.1-4 | 2026-05-29 | 2026-05-31 | Not started | 0%
OI.6 | Open items | All | Line-level reconciliation Odoo vs. legacy | [employee] | OI.5 | 2026-05-31 | 2026-05-31 | Not started | 0%
ST.1 | Stock | All | Physical count schedule + instructions | Ops | MD.7 | 2026-05-20 | 2026-05-25 | Not started | 0%
ST.2 | Stock | All | Physical count at 31-May (dry run) | Ops | ST.1 | 2026-05-29 | 2026-05-31 | Not started | 0%
ST.3 | Stock | All | Load stock lots + FIFO cost + location | [employee] | ST.2 | 2026-05-31 | 2026-05-31 | Not started | 0%
ST.4 | Stock | All | Stock valuation reconciliation Odoo vs. legacy + count | [employee] | ST.3 | 2026-05-31 | 2026-06-01 | Not started | 0%
ST.5 | Stock | NO | Norwegian SPA-held raw-material lots — load to dedicated account | [employee] + legal | ST.3 | 2026-05-31 | 2026-05-31 | Not started | 0%
ST.6 | Stock | NO | SPA holdings — line-by-line validation with legal | [employee] + legal | ST.5 | 2026-05-31 | 2026-06-01 | Not started | 0%
SM.1 | Slow-mover | All | Design decision: storage (field vs. model) | [dev] + Olivier | P1.11 | 2026-05-05 | 2026-05-10 | Not started | 0%
SM.2 | Slow-mover | All | Design decision: trigger (age / turnover / manual) | [dev] + Olivier | P1.11 | 2026-05-05 | 2026-05-10 | Not started | 0%
SM.3 | Slow-mover | All | Build lot-level provision mechanism | [dev] | SM.1,SM.2 | 2026-05-10 | 2026-05-31 | Not started | 0%
SM.4 | Slow-mover | All | Test on ≥50 lots vs. current Excel | [employee] + [dev] | SM.3 | 2026-05-31 | 2026-06-10 | Not started | 0%
SM.5 | Slow-mover | All | Compute transition delta (01-Jul) and share with auditor | Olivier | SM.4 | 2026-06-10 | 2026-06-15 | Not started | 0%
SPA.1 | SPA unwind | All | Model transition JE (30-Jun close / 01-Jul open) | Olivier + [employee] | ST.6 | 2026-06-01 | 2026-06-10 | Not started | 0%
SPA.2 | SPA unwind | All | Auditor review of transition JE | Olivier | SPA.1 | 2026-06-10 | 2026-06-15 | Not started | 0%
DR.1 | Dry run | All | Produce reconciliation pack per entity | [employee] | OI.6,ST.4,ST.6 | 2026-06-01 | 2026-06-01 | Not started | 0%
DR.2 | Dry run | All | Dry-run sign-off — per entity | Olivier | DR.1 | 2026-06-01 | 2026-06-01 | Not started | 0%
DR.3 | Dry run | All | Remediation of dry-run issues | [employee] | DR.2 | 2026-06-02 | 2026-06-20 | Not started | 0%
CM.1 | Change mgmt | — | Auditor pre-clearance meeting | Olivier | — | 2026-04-25 | 2026-05-05 | Not started | 0%
CM.2 | Change mgmt | — | Auditor written position: SPA unwind | Olivier | CM.1 | 2026-05-05 | 2026-05-15 | Not started | 0%
CM.3 | Change mgmt | — | Auditor written position: lot-level slow-mover | Olivier | CM.1 | 2026-05-05 | 2026-05-15 | Not started | 0%
CM.4 | Change mgmt | — | Auditor written position: Anglo-Saxon presentation | Olivier | CM.1 | 2026-05-05 | 2026-05-15 | Not started | 0%
CM.5 | Change mgmt | — | Tax / customs review (BE + NO VAT, Intrastat) | Olivier + tax | — | 2026-04-25 | 2026-05-01 | Not started | 0%
CM.6 | Change mgmt | — | Supplier notices drafted + reviewed (legal) | Procurement | — | 2026-05-10 | 2026-05-20 | Not started | 0%
CM.7 | Change mgmt | — | Supplier notices sent | Procurement | CM.6 | 2026-05-20 | 2026-06-01 | Not started | 0%
CM.8 | Change mgmt | — | Customer notices drafted + reviewed (legal) | Sales + Legal | — | 2026-05-10 | 2026-05-20 | Not started | 0%
CM.9 | Change mgmt | — | Customer notices sent (≥30 days before 01-Jul) | Sales + Legal | CM.8 | 2026-05-20 | 2026-06-01 | Not started | 0%
CM.10 | Change mgmt | — | Internal training — finance / ops / IT | Employee owner | — | 2026-06-15 | 2026-06-25 | Not started | 0%
GL.1 | Go-live prep | All | Refresh open AR/AP/PO/SO to 30-Jun | [employee] | DR.3 | 2026-06-26 | 2026-06-30 | Not started | 0%
GL.2 | Go-live prep | All | Refresh stock physical count to 30-Jun | Ops | DR.3 | 2026-06-27 | 2026-06-30 | Not started | 0%
GL.3 | Go-live prep | All | Refresh opening BS to 30-Jun (MVGL fallback) | [employee] | DR.3 | 2026-06-28 | 2026-06-30 | Not started | 0%
GL.4 | Go-live prep | — | Go/no-go decision (Green / Amber / Red) | Olivier | GL.1-3 | 2026-06-25 | 2026-06-25 | Not started | 0%
GL.5 | Go-live | All | Post SPA unwind transition JE | Olivier + [employee] | GL.4 | 2026-07-01 | 2026-07-01 | Not started | 0%
GL.6 | Go-live | All | Open new flow transactions (BE direct) | All | GL.5 | 2026-07-01 | 2026-07-01 | Not started | 0%
PG.1 | Post go-live | All | Hypercare — daily stand-up week 1 | All | GL.6 | 2026-07-01 | 2026-07-08 | Not started | 0%
PG.2 | Post go-live | All | H1 detail rework (if Amber at go-live) | [employee] | GL.6 | 2026-07-08 | 2026-10-31 | Not started | 0%
PG.3 | Post go-live | All | Legacy read-only access confirmed through 31-Dec-2026 | IT | GL.6 | 2026-07-01 | 2026-07-15 | Not started | 0%

## Reconciliation Pack
Reconciliation Pack — per entity, per check
Produce for each dry-run and go-live. Sign-off before closing the run.
Entity | Check | Period / date | Legacy amount | Odoo amount | Variance | Variance % | Sign-off | Preparer | Reviewer
BNV | Trial balance (Odoo vs. legacy) |  | 0 | 0
BNV | AR aging (Odoo vs. legacy) |  | 0 | 0
BNV | AP aging (Odoo vs. legacy) |  | 0 | 0
BNV | Open PO line count + value |  | 0 | 0
BNV | Open SO line count + value |  | 0 | 0
BNV | Stock valuation (Odoo vs. legacy) |  | 0 | 0
BNV | Stock physical count vs. Odoo |  | 0 | 0
NO #1 | Trial balance (Odoo vs. legacy) |  | 0 | 0
NO #1 | AR aging (Odoo vs. legacy) |  | 0 | 0
NO #1 | AP aging (Odoo vs. legacy) |  | 0 | 0
NO #1 | Open PO line count + value |  | 0 | 0
NO #1 | Open SO line count + value |  | 0 | 0
NO #1 | Stock valuation (Odoo vs. legacy) |  | 0 | 0
NO #1 | Stock physical count vs. Odoo |  | 0 | 0
NO #1 | Norwegian SPA lots — line-by-line |  | 0 | 0
NO #2 | Trial balance (Odoo vs. legacy) |  | 0 | 0
NO #2 | AR aging (Odoo vs. legacy) |  | 0 | 0
NO #2 | AP aging (Odoo vs. legacy) |  | 0 | 0
NO #2 | Open PO line count + value |  | 0 | 0
NO #2 | Open SO line count + value |  | 0 | 0
NO #2 | Stock valuation (Odoo vs. legacy) |  | 0 | 0
NO #2 | Stock physical count vs. Odoo |  | 0 | 0
NO #2 | Norwegian SPA lots — line-by-line |  | 0 | 0

## Risk Log
Risk Log
Update weekly. Red or Amber risks discussed on the Monday call.
ID | Risk | Impact | Probability | RAG | Owner | Mitigation | Status | Last updated
R1 | Simultaneous system migration + business-model flip on 01-Jul | High | Medium | Amber | Olivier | Treat as 2 independent workstreams; consider silent stabilisation window pre-01-Jul | Open
R2 | Slow-mover provision delta (Excel vs. per-lot) material | Medium | High | Amber | Olivier | Model in April, not June; share with auditor early | Open
R3 | Auditor pre-clearance not obtained | High | Medium | Red | Olivier | Initiate conversation April; block go-live if no written position | Open
R4 | Customer / supplier comms late — invoicing chaos in July | High | Medium | Amber | Sales / Procurement | Notices sent by 01-Jun; follow-up calls last week of June | Open
R5 | CoA mapping ambiguities | Medium | Medium | Amber | [employee] | Freeze mapping during P1; changes after require re-validation | Open
R6 | FX treatment ambiguity NO/BE | Medium | Medium | Amber | Olivier | Lock policy (monthly close vs. daily rate) before loading JEs | Open
R7 | Stock cut-off accuracy at 30-Jun | High | Medium | Amber | Ops | Physical count under controlled conditions; second count if variance > threshold | Open
R8 | Legacy export quality | Medium | Medium | Amber | [employee] | Demand sample exports in week 1; do not wait for full extract | Open
R9 | Norway entity legal setup incomplete at P1 | High | Low | Amber | Olivier + legal | Verify registrations, VAT numbers, bank accounts before P1 starts | Open
R10 | Bank rec breakage on H1 reload | Medium | Medium | Amber | [employee] | Defer bank rec on reloadable H1 transactions; lock policy at go-live | Open

## Change Management
Change Management Log
Track auditor, tax, supplier, customer and internal communications.
Audience | Recipient / firm | Topic | Action | Owner | Planned date | Sent / done | Response / status
Auditor | [audit firm] | Pre-clearance meeting | Discuss scope: SPA unwind, slow-mover method, Anglo-Saxon presentation | Olivier | 2026-04-25
Auditor | [audit firm] | Written position: SPA unwind | Obtain letter confirming treatment | Olivier | 2026-05-15
Auditor | [audit firm] | Written position: lot-level slow-mover | Obtain letter confirming estimate vs. policy | Olivier | 2026-05-15
Auditor | [audit firm] | Written position: Anglo-Saxon presentation | Obtain letter on BS/PL re-presentation impact | Olivier | 2026-05-15
Tax advisor BE | [tax firm] | VAT + Intrastat review — new BE direct flow | Confirm registrations, filing requirements | Olivier + tax | 2026-05-01
Tax advisor NO | [tax firm] | VAT + transfer pricing — SPA unwind + reduced NO flow | Confirm continuing registrations + TP doc | Olivier + tax | 2026-05-01
Customs | [customs broker] | New flow from 01-Jul — customs classification | Confirm EORI / declarations | Procurement + broker | 2026-05-10
Suppliers | [top 20 vendors] | New PO / VAT / bank from 01-Jul | Formal notice + master data refresh | Procurement | 2026-06-01
Customers | [top N customers] | New invoicing entity / VAT / bank from 01-Jul | Formal notice ≥30 days before; contract update if needed | Sales + Legal | 2026-06-01
Internal — Finance | Team | Training on new CoA, provision workflow, reports | Walk-through + Q&A | Employee owner | 2026-06-20
Internal — Ops | Team | Stock count procedure + lot tracking | Walk-through | Ops lead | 2026-06-20
Internal — IT | Team | Hypercare rota + escalation paths | Define rota | IT lead | 2026-06-25

## Go-NoGo
Go / No-Go Checklist
Reviewed at dry-run (01-Jun) and go-live (01-Jul). Each item must be Green for go-live.
# | Criterion | Status | Owner | Evidence / link | Notes
1 | Norway CoA + company settings live in staging (Priority 1 complete)
2 | Master data loaded and signed off
3 | Opening BS matches audited close — all 3 entities
4 | YTD TB reconciled ≥4 closed months (dry run) / 6 months (go-live)
5 | Open items loaded and aged correctly vs. legacy
6 | Stock reconciled physical ↔ valuation ↔ GL
7 | SPA holdings validated by legal
8 | Per-lot slow-mover provision tested on ≥50 lots vs. Excel
9 | Auditor written positions obtained (3 topics)
10 | SPA unwind transition JE modelled and reviewed
11 | Supplier notices sent ≥30 days before 01-Jul
12 | Customer notices sent ≥30 days before 01-Jul
13 | Tax registrations confirmed for new flow (BE + NO + customs)
14 | MVGL dataset (30-Jun snapshot) signed off
15 | Batch-tagging mechanism implemented (H1 rework possibility)
16 | Period-close policy documented (H1 stays open)
17 | Legacy read-only access confirmed through 31-Dec-2026
18 | Hypercare rota defined
19 | Training complete — finance / ops / IT
20 | Go / no-go decision recorded in writing